## Project Kickoff
Task | Details
Understand the project objectives | Create a platform for learning Agile values and principles. Provide interactive examples and a collaboration feature.
Assign roles | Scrum Master, Developers, Tester, etc.
Define the project scope and hold a kickoff meeting | Outline scope and ensure team alignment.
Clarify requirements with the instructor (Product Owner) | Confirm requirements and expectations.

## Epics and Features
Epic | Feature | Story | subtasks for stories
Create a web-based platform to educate and engage users about Agile Manifesto | Homepage for Agile Manifesto | Story 1.1: Design and implement a visually appealing homepage Story 1.2: Add an introduction to Agile and its history Story 1.3: Include navigation to other sections. | 1.1: Design and implement a visually appealing homepage 1.1.1: Create wireframes for the homepage. 1.1.2: Develop HTML and CSS for the layout. 1.1.3: Integrate animations using JavaScript. 1.1.4: Conduct user testing and gather feedback.
Create a web-based platform to educate and engage users about Agile Manifesto | Agile Values and Principles | Story 2.1: Display the four core Agile values Story 2.2: Explain the 12 principles interactively Story 2.3: Add examples to illustrate values and principles.
Create a web-based platform to educate and engage users about Agile Manifesto | Resource Library | Story 3.1: Design a library for Agile practices Story 3.2: Include downloadable resources Story 3.3: Add search/filter functionality.
Create a web-based platform to educate and engage users about Agile Manifesto | Collaboration Features | Story 4.1: Create a discussion forum Story 4.2: Enable commenting on resources Story 4.3: Implement user authentication. | 4.2: Enable users to comment on resources and principles 4.2.1: Design the comment input field and UI. 4.2.2: Develop backend APIs for storing comments. 4.2.3: Implement frontend integration with APIs. 4.2.4: Test the comment functionality.

## Sprint Planning
Sprint | Objective | Story Points
1 | Complete the Homepage for Agile Manifesto | 5, 8, 5
2 | Build the Agile Values and Principles section | 5, 8, 5
3 | Develop the Resource Library | 5, 5, 5
4 | Implement Collaboration Features and perform final testing | 8, 8, 5

## Daily Stand-ups
Daily Activity
Discuss what was completed yesterday.
Plan today's work.
Identify blockers or issues.

## Sprint Retrospectives
Aspect | Details
What went well | Team collaboration and clear communication.
What could be improved | Better time estimation for tasks.
Actionable steps | Incorporate lessons learned for future sprints.